## Sheet1
Milestone | Description | Estimated Finish
Write thesis proporsal First RNN model | Implementation of the paper: https://arxiv.org/pdf/1511.05942.pdf Using Santander dataset. Research literature and prepare research questions (improvement of baseline implementation). | 2017-03-08
Presentation Uva-PEGA RNN model improved | Based on research questions, use Santander dataset to explore the different implementations/improvement proposed. Obtain feedback from presentation Depend on the situation we could add another dataset here | 2017-04-11
Evaluation on different datasets and comparisson with baseline model / ML Learning model with handcrafted features | Use feedback obtained in the middle presention and expand the research on other datasets | 2017-05-10
First version thesis | Write thesis At the same time, different options can be considered. Eg: - analyse computational impact - implementation in PEGA systems | 2017-06-21
Finished thesis | Evangelos not available from (mid?) July | 2017-07-15