## Sheet1
Milestone | Estimated Finish
Implementation of the paper: https://arxiv.org/pdf/1511.05942.pdf Using Santander dataset Research literature and prepare research questions. Write proporsal of the thesis | 2017-03-08
Based on research questions, use Santander data set the different implementations proposed | 2017-04-05
Expand the research on other datasets | 2017-05-03
Write thesis / analyse computational impact / implement and/or analyse system in PEGA | 2017-06-21